## Risk Log Template
Project Name: |  | Kittitas Co. GIS Strategic Plan
Scale: 1 (lowest) to 4 (highest)
Identification |  |  |  | Assessment |  |  |  | Evaluation | Response
ID | Category | Risk Name | Description | Impact | Probability | Consequence | Combined Score | Rank | Prevention Plan | Contingency Plan | Residual Impact | Owner
R001 | Resources | Turnover | Losing staff and in-house GIS skill could jeopardize the implementation of the strategic plan and ongoing maintenance activities. | 4. GIS user experience could be degraded, data accuracy would decrease. Emergency response and disaster recovery operations which rely on GIS would be slower and less accurate. | 3. The county already has documented issues with retention and upskilling. | 3. Loss of data quality and experience leads to utility and confidence in GIS, creating a feedback loop of increased turnover. | 10 | High | Increase funding to expand staffing, offer training and conference attendance to upskill existing personnel. | Hire contractors to bridge the gap caused by employees departing the county. | Contractors will likely cost the county more money than equivalent in-house staff, and they have no incentive to remain with the county. | HR, GIS manager, budget and finance
R002 | Resources | Funding | Securing a sustainable funding source is listed as a critical success factor for impending hardware and software upgrades. | 4. As Esri deprecates and ends support for various software, the county must upgrade to ensure security and performance. Lack of funding would prevent future investment in enterprise GIS tooling. | 2. Per the plan, "GIS is a central service in the general budget." It is unlikely that GIS funding would completely disappear, but it is also important to ensure that there is enough funding for upgrades and staff. | 4. If funding is not secured, applications, data, and products will go offline or be vulnerable to breaches. Additionally, personnel will suffer, increasing the risk of R001 (Turnover). | 10 | High | Demonstrate use of GIS benefits and cost savings to decision-makers, and attempt to have GIS codified as a mandatory service. | Triage existing products and services, and ensure that critical operations remain functional. Inform jurisdictions and the public on which programs must be cut. | If GIS funding lapses, mission- and public-safety-critical operations will continue. GIS may fragment into different departments or units. | GIS manager, budget and finance
I001 | Infrastructure | Deprecation and Migration | Migration errors or lack of urgency to reduce dependency on outdated software. | 3. Remaining on old software opens the county to security risks and means that new toolsets are not available to GIS personnel. | 3. Because GIS is not centralized and has users across departments and locations, it can be hard to coordinate migration and upgrade. | 4. As software continues to advance, databases will be unable to communicate with applications, and workflows will begin to break. | 10 | High | Begin to send out surveys to all licensed GIS users to determine the uses of legacy software across the organization. Determine if an upgrade to ArcGIS Pro is necessary, or if another tool will suit their needs once ArcMap is deprecated. | Identify workflows which are still using outdated software, and prioritize. All new changes must be for ArcPro or Experience Builder, not ArcMap or Web App Builder. | Even with a small number of machines running outdated software, triaging outdated workflows means that critical workflows will be migrated first. Gaps in data and application uptime will occur on less-integral products. | GIS manager
OP001 | Operational | Governance and Quality Control | Lack of data governance and quality control procedures could lead to accuracy and accountability issues. | 2. Though workflows likely won't break, data quality issues reduce trust in and cost savings of GIS. | 4. Currently, there are not many existing governance structures. This means that any GIS user could publish inaccurate data, or applications could be published without a thorough, proper review. | 3. Poor GIS data quality, as mentioned in section 4.5.2, could open the county up to lawsuits and appeals. This costs money and reduces the effectiveness of GIS in the enterprise. | 9 | Medium | Begin to build data governance structures, including application and data review committees, implementing least privilege, and establishing accountability for datasets where necessary. | Establish a protocol to handle data correction. If a data error is reported or otherwise identified, this protocol will inform stakeholders, correct the error(s), and identify an accountable party for the future. | Despite governance structures and a correction protocol, minor data inaccuracies may still occur due to human error. These errors could cause temporary, low-level operational disruptions before being resolved by the established protocol. | GIS manager, technical staff
OP002 | Operational | Lack of organizational adoption | Some departments are resistant to adoption and integration of GIS workflows. | 2. These departments already have business practices to complete their work. Though GIS could lend efficiency and cost savings, it's not mission critical. | 2. Though some departments are resistant, many across the enterprise are willing to integrate GIS into their processes. | 2. The county may not be able to gain as much efficiency as otherwise possible from its GIS investment. | 6 | Medium | Demonstrate the utility of GIS across the organization, and be willing to offer suggestions if these departments approach with questions. | Provide support to other units within the organization, and be prepared to assist resistant departments if necessary. | Even with support offered, some departments may persist with inefficient workflows, resulting in ongoing operational silos and unrealized cost savings for the county. | GIS manager
S001 | Scope | Project overload and priority dilution | If GIS is centralized under IT, requests from other departments could inundate personnel and reduce effectiveness of prioritization. | 2. GIS personnel will be slower to respond, and morale may drop. Existing processes should see no impact, but maintenance may also slow. | 3. If GIS is centralized, but the number of projects remains constant or increases, staff burnout and dilution of organizational priorities is a likely conclusion. | 3. Slowing of GIS process and workflow development would reduce the benefit seen by the county. Additionally, low employee morale increases the probability of R001. | 8 | Medium | Establish clear and realistic mission and vision statements for GIS within the organization. By ensuring that there is a defined direction for the program to be moving in, priority dilution can be mitigated. | Implement a process (not unlike the risk assessment) to determine which requests to handle first and which requests align with the mission of the GIS program within the county. | If GIS is centralized and capacity does not increase to account for the increased requests from other departments, then less critical projects will be put on the back burner. | GIS manager, business unit managers
OP003 | Operational | Siloing and insufficient communication | Departments operate as silos and do not share resources, data, or information. | 3. This leads to duplication of efforts and less effective work. | 4. Local government is near-synonymous with operational silos; it is unlikely that departments share data, let alone GIS data, without additional effort. | 3. Business units may come to different conclusions with different data, or waste time and resources completing work that other units have already completed. | 10 | High | Establish a central, enterprise GIS database and server, and be proactive about reaching out to agencies to incorporate existing datasets or build new ones to serve their goals. | Connect stakeholders in relevant departments ad-hoc, as requirements and processes are described. | Though some departments likely will not be completely open, connecting GIS personnel in different departments on an ad-hoc basis will allow for at least some cross-pollination of ideas and reduction of effort. | GIS manager, business unit managers
OP004 | Operational | Breakdown of existing collaboration | In following with OP003 and R001, a key liaison between departments could leave, causing a lapse in communication regarding critical workflows. | 3. Depending on the workflows, breakdown could be relatively minor or an emergency. | 4. R001 has established a medium-high probability of employees leaving the county; OP003 has established a high probability of poor communication between units. | 4. Breakdown in critical processes could have significant public safety implications. | 11 | High | Formalize collaborations with key stakeholders through Service Level Agreements (SLAs) or Memorandums of Understanding (MOUs). These documents will clearly define roles, responsibilities, data-sharing protocols, and communication channels to create a durable and organized framework for cooperation. | Identify systems and processes which the county cannot afford to lose, and train multiple staff on those processes, including maintenance and recovery practices. | Even with documented procedures, a sudden breakdown in collaboration could cause temporary but critical disruptions to public safety or financial services while recovery procedures are implemented. | GIS manager, stakeholders, technical personnel
S002 | Scope | Scope Creep | The county's current or planned long-term projects continue to have tasks added to them. | 3. Scope creep costs exponentially more the later into the project it is introduced. | 3. Ongoing projects are at risk of stagnation or loss of direction. Ensuring that projects are wrapped-up on time is essential. | 3. Creating a culture where scope creep is acceptable or expected is wasting taxpayer money and will yield a product with less clear direction and utility. | 9 | Medium | Ensure that IPDs and MIDLs are thorough enough to encompass scope when planning long-term projects. Create and enforce deadlines during implementation to ensure that targets are met and the scope doesn't have a chance to creep. | Implement changes requested, but attempt to compromise to reduce additional costs incurred. | Especially in departments with less GIS knowledge, scope creep will still occur. Additional staff and infrastructure costs will be incurred by the county. | GIS manager, stakeholders
I002 | Infrastructure | Web-based security risks | In following with I001 and OP001, the county's planned merge to ArcGIS web-based solutions could open them to security risks. | 4. If county systems are breached, sensitive data could leak, or critical services could be taken offline. See recent cases of 9-1-1 centers being taken offline by hackers. | 3. Though ArcGIS Portal has security measures in place, current lack of governance structure and outdated infrastructure mean that one victim of social engineering could jeopardize the entire organization. | 4. Data may be unrecoverable, and downtime in critical processes can have public safety and governmental function implications. | 11 | High | Ensure that staff who will have access to ArcGIS web environments have proper training and that least-privilege and zero-trust principles are adhered to. Implement MFA, and monitor vulnerability reports and respond accordingly. | Have a process to take or lock down sensitive information, and look into on-premise backups or infrastructure to restore some functionality immediately. | Despite best efforts, data could leave the organization and applications could face downtime. Depending on the type of attack, the county could have to deal with ransomware or other types of malware introduced via ArcGIS web interfaces. | GIS manager, Chief Information Security Officer