## Risk Log Template
Project Name: |  | City of Cayce GIS Section
Scale: 1 (lowest) to 4 (highest)
Identification |  |  |  | Assessment |  |  |  | Evaluation | Response
ID | Category | Risk Name | Description | Impact | Probability | Consequence | Combined Score | Rank | Prevention Plan | Contingency Plan | Residual Impact | Owner
I001 | Infrastructure | Initial Data Quality | During the transition away from reliance on County GIS, the City may be working with outdated or inaccurate data. Staff will need to perform data QA/QC. | 2. Unbudgeted staff hours will be required to validate and repair inherited data, diverting GIS staff from initial goal implementation. | 4. This is inevitable: as the City identifies what input data is necessary and what existing data can be re-used, quality concerns will appear. | 4. If critical utility or parcel data is inaccurate, it risks misallocated capital spending and inaccurate boundary decisions, hindering progress toward Comprehensive Plan goals. | 10 | High | Request County agencies perform a QA/QC audit of their data before sharing. | Prioritize QA/QC on critical business datasets. Train City staff on data collection tools and processes. Suspend non-critical GIS projects. | Personnel hours will be used confirming data quality instead of building GIS products and processes. GIS benefits will take longer to be realized. | GIS Manager, County GIS, GIS staff
OP001 | Operational | Lack of organizational adoption | Some departments are used to relying on County GIS structures for processes, and may be resistant to a new point of contact. | 3. If these departments continue to work with the County for GIS operations, then there will be increased fragmentation of knowledge and a lack of confidence in the City enterprise. | 3. Likely to occur in several key departments due to historical working relationships and resistance to adopting new workflows and contacts. | 2. The City may not be able to gain as much efficiency as otherwise possible from its GIS investment. Additionally, if the County is charging a fee for GIS or data usage, that fee will continue to be levied on top of City GIS operating expenses. | 8 | Medium | Proactively engage with resistant stakeholders to ensure that City GIS cen meet their existing needs. Demonstrate that processes can be sped up or enhanced with an internal section. | Allow departments to continue to work with the County, but reinforce that City GIS is able to provide similar functionality more cheaply or quicker. | Even with support offered, some departments may persist with inefficient workflows, resulting in ongoing operational silos and unrealized cost savings for the City. | GIS manager
S001 | Scope | Priority dilution | Implementation of the GIS section under City Government could lead to scope creep and dilution of priorities outlined in the Comprehensive Plan. | 3. It is essential to remain aligned with the City's priorities. This will ensure benefits are realized, and allow a City GIS section to become the central repository for location data in the enterprise. | 3. As GIS becomes more accessible to departments within the enterprise, they will want to prioritize their own goals. Particularly as information product descriptions are being created, stakeholders will want their individual priorities to be heard. | 4. If other goals are prioritized over the priorities outlined in the Comprehensive Plan, then the GIS section is no longer in alignment with the enterprise. This directly conflicts with the mission and vision of the organization, and will reduce the benefits gained by the GIS program. | 10 | High | Ensure that IPDs align with stated goals and priorities. Require that department heads and other managers directly link their requests to the Comprehensive Plan. | Accept projects from other departments which align with their personal goals, but suspend them until Comprehensive Plan priorities are recognized. | Timelines for projects which are not aligned with the Comprehensive Plan will be extended, which may exacerbate Risk OP001 as departments look externally for GIS support. | GIS manager, business unit managers
I002 | Infrastructure | Security risks | Implementation of the GIS section and infrastructure within City Government could introduce a new vector for cyberattacks. | 4. If City systems are breached, the City could be exposed to legal challenges, critical services could be taken offline or held for ransom, or sensitive data could leak. Recently, 9-1-1 centers have been targeted by cybercriminals: GIS is a huge part of emergency operations. | 3. Installing net-new systems means that security systems are up-to-date and do not have many known vulnerabilities. Probability can also be reduced by researching known vectors in GIS software, and by training staff to avoid social engineering or other common tactics. Despite this, municipal governments are targets for hackers, so probability is elevated. | 4. Data may be unrecoverable, and downtime in critical processes can have public safety and governmental function implications. This will likely exacerbate OP001, as City departments look to the County for continuity of operations. | 11 | High | Before deciding on a system design, research the security of different options. Analyze recent incidents and breaches, and identify root causes if possible. | Have a process to take or lock down sensitive information, and look into on-premise backups or infrastructure to restore some functionality immediately. | Despite best efforts, data could leave the organization and applications could face downtime. Depending on the type of attack, the City could have to deal with ransomware or other types of malware. | GIS manager, Chief Information Security Officer
R001 | Resources | Funding | Securing a sustainable funding source is listed as a critical success factor for implementing a GIS section within the City. Additionally, high one-time capital costs must be paid for initial hardware and software purchases. | 4. If funding falls through, the project will be unable to continue. | 3. It is possible that decision-makers do not see the utility of GIS. Thus, it is imperative to demonstrate that GIS will provide benefits not currently realized by the City. | 3. If funding is not secured, then the City will continue to rely on the County for GIS support. This means that GIS work will not align with Comprehensive Plan priorities, and that efficiency will continue to be decreased. | 10 | High | Demonstrate use of GIS benefits and cost savings to decision-makers. Break costs into Operational and Capital expenses, and seek external funding for capital expenses. | Continue to rely on the County for GIS support. | The priorities of the GIS support do not align with the priorities outlined in the Comprehensive Plan. | GIS manager, budget and finance

## Sheet1
Identification | ID | I001 | OP001 | S001 | I002 | R001
| Category | Infrastructure | Operational | Scope | Infrastructure | Resources
| Risk Name | Initial Data Quality | Lack of organizational adoption | Priority dilution | Security risks | Funding
| Description | During the transition away from reliance on County GIS, the City may be working with outdated or inaccurate data. Staff will need to perform data QA/QC. | Some departments are used to relying on County GIS structures for processes, and may be resistant to a new point of contact. | Implementation of the GIS section under City Government could lead to scope creep and dilution of priorities outlined in the Comprehensive Plan. | Implementation of the GIS section and infrastructure within City Government could introduce a new vector for cyberattacks. | Securing a sustainable funding source is listed as a critical success factor for implementing a GIS section within the City. Additionally, high one-time capital costs must be paid for initial hardware and software purchases.
Assessment | Impact | 2. Unbudgeted staff hours will be required to validate and repair inherited data, diverting GIS staff from initial goal implementation. | 3. If these departments continue to work with the County for GIS operations, then there will be increased fragmentation of knowledge and a lack of confidence in the City enterprise. | 3. It is essential to remain aligned with the City's priorities. This will ensure benefits are realized, and allow a City GIS section to become the central repository for location data in the enterprise. | 4. If City systems are breached, the City could be exposed to legal challenges, critical services could be taken offline or held for ransom, or sensitive data could leak. Recently, 9-1-1 centers have been targeted by cybercriminals: GIS is a huge part of emergency operations. | 4. If funding falls through, the project will be unable to continue.
| Probability | 4. This is inevitable: as the City identifies what input data is necessary and what existing data can be re-used, quality concerns will appear. | 3. Likely to occur in several key departments due to historical working relationships and resistance to adopting new workflows and contacts. | 3. As GIS becomes more accessible to departments within the enterprise, they will want to prioritize their own goals. Particuarly as information product descriptions are being created, stakeholders will want their individual priorities to be heard. | 3. Installing net-new systems means that security systems are up-to-date and do not have many known vulnerabilities. Probability can also be reduced by researching known vectors in GIS software, and by training staff to avoid social engineering or other common tactics. Despite this, municipal governments are targets for hackers, so probability is elevated. | 3. It is possible that decision-makers do not see the utility of GIS. Thus, it is imperative to demonstrate that GIS will provide benefits not currently realized by the City.
| Consequence | 4. If critical utility or parcel data is inaccurate, it risks misallocated capital spending and inaccurate boundary decisions, hindering progress toward Comprehensive Plan goals. | 2. The City may not be able to gain as much efficiency as otherwise possible from its GIS investment. Additionally, if the County is charging a fee for GIS or data usage, that fee will continue to be levied on top of City GIS operating expenses. | 4. If other goals are prioritized over the priorities outlined in the Comprehensive Plan, then the GIS section is no longer in alignment with the enterprise. This directly conflicts with the mission and vision of the organization, and will reduce the benefits gained by the GIS program. | 4. Data may be unrecoverable, and downtime in critical processes can have public safety and governmental function implications. This will likely exacerbate OP001, as City departments look to the County for continuity of operations. | 3. If funding is not secured, then the City will continue to rely on the County for GIS support. This means that GIS work will not align with Comprehensive Plan priorities, and that efficiency will continue to be decreased.
| Combined Score | 10 | 8 | 10 | 11 | 10
Evaluation | Rank | High | Medium | High | High | High
Response | Prevention Plan | Request County agencies perform a QA/QC audit of their data before sharing. | Proactively engage with resistant stakeholders to ensure that City GIS cen meet their existing needs. Demonstrate that processes can be sped up or enhanced with an internal section. | Ensure that IPDs align with stated goals and priorities. Require that department heads and other managers directly link their requests to the Comprehensive Plan. | Before deciding on a system design, research the security of different options. Analyze recent incidents and breaches, and identify root causes if possible. | Demonstrate use of GIS benefits and cost savings to decision-makers. Break costs into Operational and Capital expenses, and seek external funding for capital expenses.
| Contingency Plan | Prioritize QA/QC on critical business datasets. Train City staff on data collection tools and processes. Suspend non-critical GIS projects. | Allow departments to continue to work with the County, but reinforce that City GIS is able to provide similar functionality more cheaply or quicker. | Accept projects from other departments which align with their personal goals, but suspend them until Comprehensive Plan priorities are recognized. | Have a process to take or lock down sensitive information, and look into on-premise backups or infrastructure to restore some functionality immediately. | Continue to rely on the County for GIS support.
| Residual Impact | Personnel hours will be used confirming data quality instead of building GIS products and processes. GIS benefits will take longer to be realized. | Even with support offered, some departments may persist with inefficient workflows, resulting in ongoing operational silos and unrealized cost savings for the City. | Timelines for projects which are not aligned with the Comprehensive Plan will be extended, which may exacerbate Risk OP001 as departments look externally for GIS support. | Despite best efforts, data could leave the organization and applications could face downtime. Depending on the type of attack, the City could have to deal with ransomware or other types of malware. | The priorities of the GIS support do not align with the priorities outlined in the Comprehensive Plan.
| Owner | GIS Manager, County GIS, GIS staff | GIS manager | GIS manager, business unit managers | GIS manager, Chief Information Security Officer | GIS manager, budget and finance